## Tasks
Task ID | Task Name | Bucket Name | Progress | Priority | Assigned To | Created By | Created Date | Start date | Due date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Description
0-2SfP-gJ02S5QzNNYNAzMkAF7Op | Develop Project Website | Final Development Stage | Not started | Medium | POROGAMA K.K.S.K. it22156006;LAKSHAN R H R it22917416 | PERERA A K I R it22308252 | 03/07/2026 |  | 04/26/2026 | false | true |  |  | 0/3 | Design website layout;Upload project details;Design website layout | Green
5hVi3X3zokaon00iHT6Z6ckAA82H | Progress Presentation I Preparation | Progress Tracking | Completed | Medium | LAKSHAN R H R it22917416;PERERA A K I R it22308252;POROGAMA K.K.S.K. it22156006;KONARA K.M.A.K it22350978 | PERERA A K I R it22308252 | 03/07/2026 | 11/01/2025 | 01/09/2026 | false | false | 03/07/2026 | PERERA A K I R it22308252 | 3/3 | Conduct practice session;Prepare prototype demo;Prepare presentation slides | Purple
9gFAosNMtESMt39MAPx-yckAJfWd | Final Report Writing | Final Development Stage | Not started | Medium | PERERA A K I R it22308252 | PERERA A K I R it22308252 | 03/07/2026 |  | 04/26/2026 | false | true |  |  | 0/3 | Write implementation chapter;Write methodology chapter;Write implementation chapter | Blue
BY0wyz2fTUCkbZh06O_eoMkALG6m | Conduct Brainstorming Workshop | Initiation & Planning | Completed | Medium | POROGAMA K.K.S.K. it22156006;LAKSHAN R H R it22917416;KONARA K.M.A.K it22350978;PERERA A K I R it22308252 | PERERA A K I R it22308252 | 03/07/2026 | 08/01/2025 | 08/03/2025 | false | false | 03/07/2026 | PERERA A K I R it22308252 | 3/3 | Select best project idea;Identify possible research areas;Discuss transportation problems | Yellow
BcufZ9okw0ObAkOpvNfClMkAIqHh | Prepare System Demonstration | Progress Presentation II | Completed | Medium | POROGAMA K.K.S.K. it22156006;LAKSHAN R H R it22917416;KONARA K.M.A.K it22350978;PERERA A K I R it22308252 | PERERA A K I R it22308252 | 03/07/2026 |  | 03/08/2026 | false | false | 03/07/2026 | PERERA A K I R it22308252 | 3/3 | Prepare demo scenario;Prepare demo scenario;Test each functionality | Green
BwkpE3ezSk-I-PCTgPGurskAIlOC | Final Presentation Preparation | Final Evaluation & VIVA | In progress | Medium | PERERA A K I R it22308252 | PERERA A K I R it22308252 | 03/07/2026 | 03/10/2026 | 04/23/2026 | false | true |  |  | 0/3 | Prepare final slides;Practice presentation;Prepare system demo | Purple
E7XMzoCrV06UBNd_N89TKMkAPITx | Maintain Research Logbook | Final Development Stage | Completed | Medium | POROGAMA K.K.S.K. it22156006;LAKSHAN R H R it22917416;KONARA K.M.A.K it22350978;PERERA A K I R it22308252 | KONARA K.M.A.K it22350978 | 04/01/2026 |  | 04/07/2026 | false | false | 04/10/2026 | KONARA K.M.A.K it22350978 | 0/3 | Document meetings;Record weekly progress;Document development activities | Blue
FgOtyfiZckqDr97uEkY7IckAMRQ7 | Define Research Problem | Initiation & Planning | Completed | Medium | KONARA K.M.A.K it22350978;LAKSHAN R H R it22917416;PERERA A K I R it22308252;POROGAMA K.K.S.K. it22156006 | PERERA A K I R it22308252 | 03/07/2026 | 08/06/2025 | 08/06/2025 | false | false | 03/07/2026 | PERERA A K I R it22308252 | 3/3 | Document problem statement;Identify road safety issues;Define project scope | Yellow
G5qdIQIFbUODvLX7x6MwR8kAMC4M | Submit Research Paper | Research Paper Preparation | In progress | Medium | LAKSHAN R H R it22917416;PERERA A K I R it22308252 | PERERA A K I R it22308252 | 03/07/2026 |  | 05/04/2026 | false | false |  |  | 0/3 | Record submission confirmation;Prepare final version;Submit paper | Red
H1pGhurECUiEwDyIHnfsn8kABQ9u | Review and Edit Paper | Research Paper Preparation | In progress | Medium | LAKSHAN R H R it22917416;PERERA A K I R it22308252;POROGAMA K.K.S.K. it22156006 | PERERA A K I R it22308252 | 03/07/2026 | 01/18/2026 | 05/01/2026 | false | false |  |  | 0/3 | Correct formatting;Proofread content;Apply supervisor feedback | Blue
MJkNzsisS0m33BCBgqEPxMkAIa_0 | Finalize Proposal Report | Proposal Stage | Completed | Medium | LAKSHAN R H R it22917416;PERERA A K I R it22308252;POROGAMA K.K.S.K. it22156006;KONARA K.M.A.K it22350978 | PERERA A K I R it22308252 | 03/07/2026 | 09/18/2025 | 09/23/2025 | false | false | 03/07/2026 | PERERA A K I R it22308252 | 3/3 | Submit final proposal;Apply supervisor corrections;Format document | Blue
QXbKMy-sjk-5Urdm0ez2OMkAKQML | Maintain Research Logbook | Final Development Stage | Completed | Medium | POROGAMA K.K.S.K. it22156006;LAKSHAN R H R it22917416;KONARA K.M.A.K it22350978;PERERA A K I R it22308252 | KONARA K.M.A.K it22350978 | 04/10/2026 |  | 05/07/2026 | false | false | 04/10/2026 | KONARA K.M.A.K it22350978 | 0/3 | Document meetings;Record weekly progress;Document development activities | Blue
TDWgglNFP0ad1b1NGov_FskAKZsi | Submit Checklist I | Progress Tracking | Completed | Medium | LAKSHAN R H R it22917416;PERERA A K I R it22308252 | PERERA A K I R it22308252 | 03/07/2026 | 10/01/2025 | 01/09/2026 | false | false | 03/08/2026 | PERERA A K I R it22308252 | 2/3 | Update task progress;Export planner report;Submit checklist | Blue
UmeEA7wLBE-L9xn_x03wSskACCOr | Proposal Presentation Preparation | Proposal Stage | Completed | Medium | POROGAMA K.K.S.K. it22156006;LAKSHAN R H R it22917416;KONARA K.M.A.K it22350978;PERERA A K I R it22308252 | PERERA A K I R it22308252 | 03/07/2026 | 09/12/2025 | 03/20/2026 | false | false | 03/07/2026 | PERERA A K I R it22308252 | 3/3 | Prepare slides;Practice presentation;Prepare system diagrams | Purple
VIM1vudT8U2IHHm6ePD_88kAMBHC | System Integration | Final Development Stage | Completed | Medium | POROGAMA K.K.S.K. it22156006;LAKSHAN R H R it22917416;KONARA K.M.A.K it22350978;PERERA A K I R it22308252 | PERERA A K I R it22308252 | 03/07/2026 |  | 03/08/2026 | false | false | 04/01/2026 | KONARA K.M.A.K it22350978 | 0/3 | Integrate ML model with system;Connect database;Connect database | Green
VzAGm3TPu0OSOwMLmuogQMkALCxs | Prepare Research Paper Outline | Research Paper Preparation | In progress | Medium | LAKSHAN R H R it22917416;PERERA A K I R it22308252;POROGAMA K.K.S.K. it22156006;KONARA K.M.A.K it22350978 | PERERA A K I R it22308252 | 03/07/2026 | 01/18/2026 | 05/01/2026 | false | false |  |  | 0/3 | Define sections;Assign writing responsibilities;Draft outline | Orange
WFK22fAckE6ihUoZ2R-MJ8kAES0W | Define Research Objectives | Proposal Stage | Completed | Medium | POROGAMA K.K.S.K. it22156006;LAKSHAN R H R it22917416;KONARA K.M.A.K it22350978;PERERA A K I R it22308252 | PERERA A K I R it22308252 | 03/07/2026 | 08/25/2025 | 08/27/2025 | false | false | 03/07/2026 | PERERA A K I R it22308252 | 3/3 | Define research goals;Document objectives;Define system requirements | Orange
_0uTTp13wE2YEbcR302t78kAHPpz | Complete Topic Assessment Form (TAF) | Initiation & Planning | Completed | Medium | KONARA K.M.A.K it22350978;LAKSHAN R H R it22917416;PERERA A K I R it22308252;POROGAMA K.K.S.K. it22156006 | PERERA A K I R it22308252 | 03/07/2026 | 08/07/2025 | 08/10/2025 | false | false | 03/07/2026 | PERERA A K I R it22308252 | 3/3 | Review with supervisor;Fill TAF template;Submit TAF | Yellow
b-yyjJFakkizk9lK00_11ckADfM5 | Final Report Completion | Progress Presentation II | Completed | Medium | LAKSHAN R H R it22917416;PERERA A K I R it22308252 | PERERA A K I R it22308252 | 03/07/2026 |  | 04/26/2026 | false | false | 03/07/2026 | PERERA A K I R it22308252 | 3/3 | Apply corrections;Final formatting;Final formatting | Blue
e41tZPU5rUuol5-nHl0rLckAEPYV | Prepare Proposal Report (Draft) | Proposal Stage | Completed | Medium | POROGAMA K.K.S.K. it22156006;LAKSHAN R H R it22917416;KONARA K.M.A.K it22350978;PERERA A K I R it22308252 | PERERA A K I R it22308252 | 03/07/2026 | 09/05/2025 | 09/14/2025 | false | false | 03/07/2026 | PERERA A K I R it22308252 | 4/4 | Write proposed methodology;Add references;Write introduction;Write problem statement | Blue
fECak4N84EasEqDiocumFMkAIWRp | Maintain Research Logbook | Final Development Stage | Completed | Medium | POROGAMA K.K.S.K. it22156006;LAKSHAN R H R it22917416;KONARA K.M.A.K it22350978;PERERA A K I R it22308252 | KONARA K.M.A.K it22350978 | 04/10/2026 |  | 06/07/2026 | false | false | 04/27/2026 | KONARA K.M.A.K it22350978 | 0/3 | Document meetings;Record weekly progress;Document development activities | Blue
hV5gR9s-xEOqjyGV2qpnJ8kAK4f3 | Write Research Paper Draft | Research Paper Preparation | In progress | Medium | PERERA A K I R it22308252 | PERERA A K I R it22308252 | 03/07/2026 | 01/18/2026 | 05/01/2026 | false | false |  |  | 0/3 | Write methodology;Write introduction;Write literature review | Blue
jXYnMp6b_U2B0p8dalKKsMkAFsgy | Design System Architecture | Proposal Stage | Completed | Medium | POROGAMA K.K.S.K. it22156006;LAKSHAN R H R it22917416;KONARA K.M.A.K it22350978;PERERA A K I R it22308252 | PERERA A K I R it22308252 | 03/07/2026 | 09/05/2025 | 09/05/2025 | false | false | 03/07/2026 | PERERA A K I R it22308252 | 3/3 | Define system modules;Create architecture diagram;Define data flow | Green
juelr3vjH0GP_UycL8xLjskAG5vF | Dataset Collection | Progress Tracking | Completed | Medium | POROGAMA K.K.S.K. it22156006;LAKSHAN R H R it22917416;KONARA K.M.A.K it22350978;PERERA A K I R it22308252 | PERERA A K I R it22308252 | 03/07/2026 | 09/23/2025 | 09/23/2025 | false | false | 03/07/2026 | PERERA A K I R it22308252 | 3/3 | Download datasets;Organize dataset;Identify dataset sources | Orange
kb8HKokI1U2FDBC-V_NxkckAML-S | Conduct Literature Review | Proposal Stage | Completed | Medium | POROGAMA K.K.S.K. it22156006;LAKSHAN R H R it22917416;KONARA K.M.A.K it22350978;PERERA A K I R it22308252 | PERERA A K I R it22308252 | 03/07/2026 | 08/18/2025 | 08/30/2025 | false | false | 03/07/2026 | PERERA A K I R it22308252 | 3/3 | Review similar systems;Search academic research papers;Identify research gaps | Orange
liv-UT1eYE6CTcnYbNwVtckAK6V7 | Submit Checklist II | Progress Presentation II | Completed | Medium | POROGAMA K.K.S.K. it22156006;LAKSHAN R H R it22917416;KONARA K.M.A.K it22350978;PERERA A K I R it22308252 | PERERA A K I R it22308252 | 03/07/2026 |  | 03/10/2026 | false | false | 04/01/2026 | KONARA K.M.A.K it22350978 | 2/3 | Export planner report;Update planner progress;Submit checklist | Red
nV-FhMPLwEWd7u13KdS-wskAMx5v | Conduct Needs Analysis | Proposal Stage | Completed | Medium | POROGAMA K.K.S.K. it22156006;LAKSHAN R H R it22917416;KONARA K.M.A.K it22350978;PERERA A K I R it22308252 | PERERA A K I R it22308252 | 03/07/2026 | 08/18/2025 | 08/22/2025 | false | false | 03/07/2026 | PERERA A K I R it22308252 | 3/3 | Prepare for data gathering;Collect information;Evaluate information | Orange
pPG-lGAqsUCaJc8C6fW6oMkAAbpv | Maintain Research Logbook | Final Development Stage | Completed | Medium | POROGAMA K.K.S.K. it22156006;LAKSHAN R H R it22917416;KONARA K.M.A.K it22350978;PERERA A K I R it22308252 | PERERA A K I R it22308252 | 03/07/2026 |  | 03/30/2026 | false | false | 04/01/2026 | KONARA K.M.A.K it22350978 | 3/3 | Document meetings;Record weekly progress;Document development activities | Blue
rGa51busNUGog2TdpjQ5QckAEGav | Write Results and Discussion | Research Paper Preparation | In progress | Medium | LAKSHAN R H R it22917416;PERERA A K I R it22308252 | PERERA A K I R it22308252 | 03/07/2026 | 01/18/2026 | 05/01/2026 | false | false |  |  | 0/3 | Prepare graphs;Analyze system results;Document findings | Orange
t0kjwGdG1EWIRVxiG3C-xckAGBMh | Prepare PP2 Presentation | Progress Presentation II | Completed | Medium | PERERA A K I R it22308252 | PERERA A K I R it22308252 | 03/07/2026 | 01/16/2026 | 03/08/2026 | false | false | 03/07/2026 | PERERA A K I R it22308252 | 3/3 | Add project progress summary;Prepare slides;Add system architecture diagrams | Purple
tMp3cZMYAk-i_pjC6uX-ockAP_JB | System Testing | Final Development Stage | In progress | Medium | LAKSHAN R H R it22917416;PERERA A K I R it22308252 | PERERA A K I R it22308252 | 03/07/2026 |  | 03/08/2026 | false | true |  |  | 0/3 | Identify bugs;Fix system errors;Perform functionality testing | Green
vJks98oinEiuk7NVP3JJSMkAKsrR | Submit Final Deliverables | Final Deliverables & Project Closure | In progress | Medium | LAKSHAN R H R it22917416;PERERA A K I R it22308252;POROGAMA K.K.S.K. it22156006;KONARA K.M.A.K it22350978 | PERERA A K I R it22308252 | 03/07/2026 | 02/02/2026 | 05/01/2026 | false | false |  |  | 0/3 | Submit final documentation;Submit project website;Submit research logbook | Red
yfnhQEQOJkClah354m10OMkAEhc0 | Maintain Research Logbook | Final Development Stage | Not started | Medium | POROGAMA K.K.S.K. it22156006;LAKSHAN R H R it22917416;KONARA K.M.A.K it22350978;PERERA A K I R it22308252 | KONARA K.M.A.K it22350978 | 04/27/2026 |  | 07/07/2026 | true | false |  |  | 0/3 | Document meetings;Record weekly progress;Document development activities | Blue
ygm8C8D3GkqKuOhVL4MAXMkAALa- | Prepare Project Charter | Initiation & Planning | Completed | Medium | KONARA K.M.A.K it22350978;LAKSHAN R H R it22917416;PERERA A K I R it22308252;POROGAMA K.K.S.K. it22156006 | PERERA A K I R it22308252 | 03/07/2026 | 08/11/2025 | 08/15/2025 | false | false | 03/07/2026 | PERERA A K I R it22308252 | 3/3 | Allocate responsibilities;Define project objectives;Define milestones | Yellow
nixn4wnGVE6LEntprjIMp8kAB7eL | Develop ML Model | Progress Tracking | Completed | Medium | LAKSHAN R H R it22917416 | PERERA A K I R it22308252 | 03/07/2026 | 10/08/2025 | 10/20/2025 | false | false | 03/08/2026 | PERERA A K I R it22308252 | 3/3 | Select ML algorithm;Evaluate accuracy;Train prediction model | Green
mrW-Q4DTT06aQE0HSbNY-MkAGDMF | Develop System Prototype | Progress Tracking | Completed | Medium | POROGAMA K.K.S.K. it22156006 | PERERA A K I R it22308252 | 03/07/2026 | 10/15/2025 | 10/30/2025 | false | false | 03/08/2026 | PERERA A K I R it22308252 | 0/2 | Develop backend system;Implement detection module | Green
LviYEPByMU-SrO6Uy7jCCMkANiAt | Group Registration | Initiation & Planning | Completed | Medium | LAKSHAN R H R it22917416 | PERERA A K I R it22308252 | 03/07/2026 | 08/05/2025 | 08/05/2025 | false | false | 03/08/2026 | PERERA A K I R it22308252 | 3/3 | Verify supervisor assignment;Confirm group members;Register group in university system | Yellow
V4Mxry5T_0C9BlWFXU8OyckADIjW | Data Preprocessing | Progress Tracking | Completed | Medium | LAKSHAN R H R it22917416;KONARA K.M.A.K it22350978 | PERERA A K I R it22308252 | 03/07/2026 | 10/01/2025 | 10/10/2025 | false | false | 03/07/2026 | PERERA A K I R it22308252 | 3/3 | Clean dataset;Split training and testing data;Label data | Green

## Plan name
Plan name | IoT & ML-based Vehicle Speed Monitoring with RFID-Enabled License Validation
Plan ID | USXUTi8yl0ed3vAOKrzLMskADSiw
Date of export | 04/30/2026